## Sheet1
Done
In Progress
Omitted
Item | Topic | Particulars | Status | Next Steps | When | Responsible | Notes | Links
1 | Authentication | Implemented role-based separation on the authentication page | Done | Double-check session-to-profile mapping | 2026-04-27 | Yñikko Aguas | Separated login behavior by role
2 | Profile Mapping | Resolved profile/dashboard name mismatch bug | Done | Prevent cross-user data leakage | 2026-04-27 | Yñikko Aguas | Fixed displayed user identity across dashboard/profile
3 | Supabase Profiles | Integrated User Profiles and Role assignments with Supabase | Done | Continue validating session-to-profile mapping | 2026-04-27 | Yñikko Aguas | Foundation for role-based platform data
4 | Testing Accounts | Set up backend testing support and test staff accounts | Done | Test flows for Exonaut, Lead, Commander, and Admin | 2026-04-28 | Yñikko Aguas | Created create_test_staff_accounts.sql
5 | Mission Lifecycle | Completed mission flow from Exonaut submission to Lead grading | Done | Connect grading to automatic point events | 2026-04-28 | Yñikko Aguas | Includes feedback and point visibility for Exonauts
6 | PDF Uploads | Integrated Supabase Storage for PDF uploads | Done | Continue testing preview/open behavior | 2026-04-28 | Yñikko Aguas | Leads can open and preview submitted PDFs
7 | Admin Mission Builder | Launched Platform Admin Mission Builder | Done | Add badge/point system layer | 2026-04-28 | Yñikko Aguas | Admins can create missions that appear across role views
8 | Supabase Workflow Data | Connected missions, submissions, grades, directives, uploads, and escalations to Supabase | Done | Review RLS policies for security | 2026-04-28 | Yñikko Aguas | Major workflow data moved from static/local state
9 | Lead Directives | Built Lead-to-Exonaut directive flow | Done | Expand clarification/review handling if needed | 2026-04-28 | Yñikko Aguas | Lead creates directive, Exonaut accepts or requests clarification
10 | Community Directory | Updated Community page with Supabase-backed profiles | Done | Verify authenticated directory access | 2026-04-28 | Yñikko Aguas | Exonauts, Leads, Commanders, and Admins can see each other
11 | Commander Escalations | Updated Commander escalation views to read/update Supabase | Done | Clarify escalation vs removal workflows | 2026-04-28 | Yñikko Aguas | Supabase-backed commander operations
12 | RLS / Security | Added RLS migrations for secure Community directory access | Done | Review policies for leaderboard, kudos, and messaging | 2026-04-28 | Yñikko Aguas | Supports authenticated access control
13 | Weekly Missions | Reworked Missions flow into weekly mission structure | Done | Continue aligning submissions with weekly logic | 2026-04-29 | Yñikko Aguas | Missions now organized by week
14 | Mission Detail Pages | Defined mission detail behavior with full submission view | Done | Polish mission states and empty states | 2026-04-29 | Yñikko Aguas | Each mission opens into its own detail page
15 | Mission Status Logic | Clarified mission status using mission_submissions instead of hardcoded status | Done | Verify with real submission data | 2026-04-29 | Yñikko Aguas | More reliable status source
16 | Commander Track Progress | Built Commander Track Progress dashboard | Done | Continue improving drill-down metrics | 2026-04-29 | Yñikko Aguas | Includes track, lead, roster, submissions, points, risk, and activity
17 | Commander Drilldown | Built individual Exonaut progress drill-down for Commander | Done | Connect all metrics to source-of-truth data | 2026-04-29 | Yñikko Aguas | Commander can inspect individual progress
18 | Commander Project Progress | Built Commander Project Progress dashboard | Done | Refine project pages and progress counts | 2026-04-29 | Yñikko Aguas | Tracks project, officer, task, participant, and status metrics
19 | Pass the Crown | Clarified and added Pass the Crown logic for Track Leads | Done | Verify crown ownership controls Track Ops correctly | 2026-04-29 | Yñikko Aguas | Crown holders act as temporary Track Leads
20 | Commander/Admin Scope | Clarified Commander vs Admin responsibilities | Done | Continue separating operational permissions | 2026-04-29 | Yñikko Aguas | Improves role clarity
21 | Escalations / Removals | Clarified Escalations vs Removals workflow | Done | Finalize removal states if needed | 2026-04-29 | Yñikko Aguas | Separated issue tracking from removal decisions
22 | Rank / Tier Sync | Fixed Dashboard, Profile, Sidebar, and Leaderboard rank/tier syncing | Done | Continue testing live points calculation | 2026-05-04 | Yñikko Aguas | All areas now use same live points-based calculation
23 | Credentials | Restored Credentials badge/certificate categories | Done | Test badge detail views | 2026-05-04 | Yñikko Aguas | Clickable category cards and full badge details added
24 | Announcements / Badges | Connected Announcements, Managers, Badge Catalog, and User Badges to Supabase | Done | Apply/review related migration | 2026-05-04 | Yñikko Aguas | Local fallback included
25 | Authentication Cleanup | Removed visible test staff shortcuts and role selector buttons | Done | Keep test access internal only | 2026-05-05 | Yñikko Aguas | Cleaned up production-facing login screen
26 | Crown Transfer | Updated Pass the Crown so leads can request transfer anytime | Done | Keep Commander approval required | 2026-05-05 | Yñikko Aguas | Improved lead handoff flow
27 | Kudos Cleanup | Cleaned Kudos recipient display and corrected Admin giving label | Done | Improve kudos point impact later | 2026-05-06 | Yñikko Aguas | Names display more cleanly
28 | Database Migration | Added Supabase migration for announcements, reactions, managers, badge catalog, and user badges | Done | Run migration in Supabase environment | 2026-05-07 | Yñikko Aguas | Supports Supabase-backed platform features
29 | Track Assignment | Manually assigned Exonauts to their respective tracks | Done | Verify assignments in user profiles | 2026-05-08 | Yñikko Aguas | Improves roster and track views
30 | GitHub / Boss Repo | Pushed completed platform update to boss repo on main | Done | Continue regular commits/pushes | 2026-05-08 | Yñikko Aguas | Main branch updated | https://github.com/mackcomandante/Exonaut.git
31 | Manual Activity Credits | Fixed manual activity credits across dashboard, track pages, sidebar, profile, and summaries | Done | Align project scoring with same logic | 2026-05-11 | Yñikko Aguas | Credited track tasks now count as completed
32 | Admin Views | Updated admin views so user points and profile photos display correctly | Done | Continue checking admin user detail views | 2026-05-11 | Yñikko Aguas | Improved admin visibility
33 | Recent Manual Credits | Made Recent Manual Credits scrollable | Done | Review long-list behavior | 2026-05-12 | Yñikko Aguas | UI usability fix
34 | User Directory | Made User Directory rows clickable for admin review | Done | Improve completed task inspection | 2026-05-13 | Yñikko Aguas | Admins can view accomplished tasks per user
35 | Exonaut of the Week | Fixed Exonaut of the Week date/window logic | Done | Verify with real weekly points | 2026-05-14 | Yñikko Aguas | Aligned with weekly points
36 | Weekly Leaderboard | Updated weekly leaderboard to use actual weekly points | Done | Test filters later by cohort, track, week, and category | 2026-05-15 | Yñikko Aguas | “This Week” no longer uses lifetime totals
37 | Project Pages | Refine Project pages for consistent progress, submissions, and points | Done | Review Project Feed and Project Progress pages | 2026-05-15 | Yñikko Aguas | Needs cleanup across Exonaut, Commander, and Admin views
38 | Notifications | Fix notifications | Done | Test unread counts and realtime behavior | 2026-05-18 | Yñikko Aguas | Listed as next step from May 5
39 | Dates | Fix incorrect dates across platform | Done | Audit dashboard, EOW, mission, and project dates | 2026-05-20 | Yñikko Aguas | Some date logic already improved by May 11
40 | Dark Mode | Add dark mode | Done | Only continue if still needed | 2026-05-20 | Yñikko Aguas | Originally listed as “Maybe add dark mode”
41 | Chatbot Branding | Renamed chatbot assistant from EX-O to X-O across the chat UI | Done | Verify all helper text and labels use X-O | 2026-05-21 | Yńikko Aguas | Updated assistant header/input naming for brand consistency | exoasia-exonaut-program/project/chatbot-ui.jsx
42 | Weekly Recap | Added Weekly Recap experience that appears on the user’s first dashboard visit of the week | Done | Validate live weekly metrics with Supabase data | 2026-05-22 | Yńikko Aguas | Uses weekly window logic and local seen-state per user/week | exoasia-exonaut-program/project/dashboard.jsx
43 | Weekly Recap UI | Converted recap from dashboard card into a focused modal-style recap presentation | Done | Continue polishing mobile spacing if needed | 2026-05-25 | Yńikko Aguas | Improved recap hierarchy, metrics, next action, and dismiss/open actions | exoasia-exonaut-program/project/styles.css
44 | Badge Popup Flow | Removed badge celebration popup overlap with Weekly Recap | Done | Revisit badge celebration timing later if needed | 2026-05-26 | Yńikko Aguas | Badge popup no longer competes with the weekly recap modal | exoasia-exonaut-program/project/app.jsx
45 | Admin Account Deletion | Added admin Delete buttons for Supabase-backed user accounts in Cohort Management | Done | Test against deployed delete-user Edge Function | 2026-05-30 | Yńikko Aguas | Includes self-delete guard, confirmation, roster cleanup, and selected-user cleanup | exoasia-exonaut-program/project/admin.jsx
46 | Delete User Edge Function | Created delete-user Supabase Edge Function for admin/commander account deletion | Done | Deploy function and set SUPABASE_SERVICE_ROLE_KEY secret | 2026-06-01 | Yńikko Aguas | Function verifies caller role, prevents self-delete, cleans related rows, then deletes auth user | supabase/functions/delete-user/index.ts
47 | Delete Flow Fallback | Handled unreachable Edge Function errors with profile-row fallback and clearer admin warning | Done | Deploy Edge Function for full Supabase Auth deletion | 2026-06-03 | Yńikko Aguas | Prevents raw browser failure and explains when Auth account remains | exoasia-exonaut-program/project/supabase-profile.jsx
48 | Chatbot Fixes | Improved chatbot flow and added recruitment-related backend support Done Test chatbot responses and recruitment point behavior | Done | Polish Commander messages | 2026-06-04 | Yńikko Aguas | Chatbot and recruitment features work more reliably
49 | Commander Messages | Fixed message name display for Commander conversations Done Verify message sender names across roles | Done | Bugs have seen in the Cohort section | 2026-06-05 | Yńikko Aguas | Commander message identity displays correctly
50 | Cohort Bugs | Fixed cohort logic, hidden cohort handling, and weekly points support Done Review cohort switching and EOW calculations | Done | Project points must reflect | 2026-06-08 | Yńikko Aguas | Cohort views and weekly calculations behave more consistently
51 | Project Points | Fixed project task point handling and added backfill support Done Validate project pillar totals and approved task credits | Done | Resignation Guide must be seen in the exonaut guide | 2026-06-10 | Yńikko Aguas | Project points and task credits align with ledger data
52 | Implement Resignation Protocol | Added resignation/removal protocol and cleaned related UI flows Done Test turnover plan update and removal request handling | Done | Fix Login with Google | 2026-06-11 | Yńikko Aguas | Exonaut resignation/removal process is more complete
53 | Google Auth | Fixed Google authentication setup and auth loading behavior Done Retest Google sign-in on deployed site | Done | Profile must be clickable under community page | 2026-06-18 | Yńikko Aguas | Google login flow is more stable
54 | Profile & Community | Fixed edit profile and removed usernames under community threads | Done | Check profile save flow and community post display | 2026-06-19 | Yńikko Aguas | Profiles edit better and community posts look cleaner
55 | Collapsible Sidebar | Added collapsible sidebar behavior and responsive sidebar styling | Done | Ritual Post points clean up | 2026-06-22 | Yńikko Aguas | Navigation can collapse for more workspace room
56 | Ritual Post points | Added cascade cleanup so deleting ritual-linked posts removes ritual points | Done | Apply Supabase migration and test deleting ritual posts | 2026-06-23 | Yńikko Aguas | Ritual points are deducted when linked posts are deleted